## GIANG
GIANG — Progress Report ¦ Project 3 (Vi's Tool): Dream Company & Outreach
Note: 'Date' left blank to be filled in. Owner: Giang.
Date | Tool / Area | Type | Task | What I did | Status
| Dream Company / Outreach | Production Bugfix | Fix "Route not found" 404 on all tools | Production returned 'Route POST://api/... not found' for every feature. Root cause: BACKEND_URL had a trailing slash, so requests hit //api/... which Fastify rejects as a different route. Stripped the trailing slash in shared/env/server.ts so the path is always /api/... | Done
| Deployment / Railway | Config / Deploy | Point backend deploy at the correct branch | Backend was running an old 'claude-work' branch, frozen and out of sync with main. Got main built and deployed; confirmed Railway (backend) and Vercel (frontend) both serve the fix commit. | Done
| Production | Verification | Verify every API is live | Tested all Dream Company, Outreach and CV Optimizer endpoints on production: all return expected results (200, or 401 from auth). No more 404. | Done
| Dream Company | Code fix | Use real job listings in the roadmap | Roadmap was being generated with an empty job list. Now the live job search runs first and real, current listings are passed into the roadmap. | Done
| Dream Company | Code fix | Handle job-search outage gracefully | If the job search service fails, the user now sees a clear 'live job listings unavailable' message instead of an empty/misleading result; the roadmap still works. | Done
| Outreach | Code fix | Reject unreadable job descriptions | The job-description URL validator now rejects pages it cannot parse, instead of feeding navigation/footer junk into the generated message. | Done
| Outreach | Code fix | Add timeout + retry to URL scraping | URL scraping now times out at 15s and retries on temporary errors, so a slow or flaky page can no longer hang the whole outreach flow. | Done
| Outreach | Code fix | Enable prompt caching | Cache the static system prompt and the sender CV so repeat requests reuse them and cost fewer tokens. | Done
| Outreach | Code fix | Fix LinkedIn message cut-off | LinkedIn messages are now trimmed on word boundaries (within the character limit) so words are never cut in the middle. | Done
| Dream Company / Outreach | Code audit | Review remaining risks (no API key/token needed) | Reviewed the live code and logged 3 follow-ups: (1) the LLM timeout setting is not applied to the Anthropic client; (2) very large model outputs can hit the token limit and return a 500; (3) the Dream Company CV parser needs safer error handling. | Done
3/7 | Dream Company | Code fix | Add per-step SDK timeouts (M1.1) | createAnthropicClient() built the Anthropic client with no timeout, so a stuck request could hang ~10 min. Added env-overridable per-step SDK timeouts (analyze 30s, roles 60s, roadmap 120s, parse-cv 90s) aligned with the proxy budgets, plus maxRetries:0. A timed-out request now returns a clear 504. Other features kept SDK defaults so CV Optimizer's long calls are unaffected. | Done
3/7 | Dream Company | Code fix | Stop 500s on truncated model output (M1.2) | analyze/roles/roadmap now check stop_reason=max_tokens before parsing. A cut-off output returns a retryable 502 with a friendly message + a per-step log line, instead of a bare 500. The route was reordered so the 502 wins over the generic step->500 branch. | Done
3/7 | Dream Company | Code fix | Safer CV parser (M1.3) | parseDreamCompanyCv now wraps the final JSON.parse and checks max_tokens. A corrupted/oversized CV or bad model JSON returns a friendly 422 (too long / could not read) instead of crashing with a 500. Valid PDF and DOCX still parse correctly. | Done
3/7 | Dream Company | Verification | E2E test of M1 fixes (M1.4) | Tested on a local backend (branch not deployed yet; backend deploys from main). Real API runs: analyze->roles->roadmap all HTTP 200; forced SDK timeout->504; forced truncation->502; parse-cv wrong type->400, valid DOCX->200. Flagged 2 risks for M2: analyze ran 29.2s vs the 30s budget (thin margin); roles is the slowest step at 46s (targets M2.2). | Done (local); prod after merge
3/7 | Dream Company | Speed (M2.2) | Reduce roles 20 -> 10 + max_tokens 4096 | Cut the heaviest step. Quality-verified with a 2-profile A/B (10-list keeps the high-fit core, more diverse, drops low-fit near-duplicates). Measured 46.4s -> 25.1s (~-44%), no quality drop. | Done
3/7 | Dream Company | Investigation (M2.4) | Prompt caching assessment | Concluded not worth it: analyze/roles/parse-cv inputs are below the 1024-token cache minimum, roadmap has no static prefix, no cross-request reuse, and latency is output-bound. Documented in test/dream-company/M2.4-prompt-caching.md. | Done
3/7 | Dream Company | Speed/UX (M2.1) | SSE streaming end-to-end | Backend messages.stream + 3 SSE routes (open/delta/done/error + heartbeat), Next.js proxy passthrough (no buffering), and FE streaming client + token-driven progress bar. Verified token-by-token happy + error paths. Non-breaking (JSON endpoints kept). | Done
3/7 | Dream Company | UX (M2.3) | Progress bar + time expectations | Per-step ProgressBar driven by the real token stream + honest time hints ('~20-40s', '1-2 min for the most accurate plan'). 'Live jobs unavailable' already surfaced on the UI. | Done
3/7 | Dream Company | QA (M2.5) | E2E QA, 2 sample students | Simulated Supabase (dev project, throwaway students). Student1 JSON path 6/6; Student2 streaming path all 3 OK; edge cases (401/504/502/422/jobsError) OK. Report in test/dream-company/M2.5-qa-report.md. Final human visual round on deployed app = owner. | Done (local); prod round = human
3/7 | Dream Company | Research (M2.6) | Speed research log | Tried + logged: M2.2 fewer roles (win), M2.4 caching (rejected, justified). Model-swap to Haiku rejected earlier (quality). No duplicate attempts. | Ongoing
3/7 | Dream Company | Verification | Prod E2E after M2 merge (PR #9) | Ran the full flow on cvadvance.com with a real token: JSON analyze 26s / roles 31s (10 roles) / roadmap 55s (3 phases, 20 jobs, jobsError null) + parse-cv 3.8s; all 3 streaming endpoints OK (58/63/136 deltas). Auth gate 401, no 404/500. Confirmed M2 (streaming + 10 roles) is live and working on prod. | Done
3/7 | Dream Company | Hotfix | Preserve proxy error messages + widen analyze timeout | Two small fixes found during prod testing, merged to main. (1) http-client now reads the backend's {error} field, so parse-cv shows 'Only PDF and DOCX files are supported' instead of a generic 'Bad Request' (fix applies to all endpoints). (2) Analyze SDK timeout raised 30s -> 45s (measured ~26-29s on prod left almost no headroom); still env-overridable. Both typecheck + verified. | Done
6/7 | Dream Company | UX polish | Variable progress ceiling + rotating status text | Progress bar no longer freezes at a fixed 96% - asymptotic curve to a randomised 93-98% ceiling; the sub-status line under the bar rotates per step (perceived speed). Frontend typecheck + lint clean. | Done
6/7 | Dream Company | Reliability | Retry Anthropic 529/503 overload (streaming + non-streaming) | withRetry only retried 429; the streaming path (what production uses) had no retry at all, so a transient 'overloaded' blip showed users a bare 500. Now retries 429/529/503 on both paths with backoff + a friendly 'briefly overloaded, try again' message. 8/8 simulated-error checks pass. | Done
6/7 | Dream Company | QA / Baseline | Sonnet quality baseline - 13 test cases, per-step outputs | Ran the real flow as a user (local backend, model claude-sonnet-4-6), saved analyze/roles/roadmap output per case + a PM report. Latency ~110s, cost ~$0.089/user; strong on honesty / injection-resistance / no-fabrication / localization. | Done
6/7 | Dream Company | A/B model test | Sonnet vs Haiku 4.5 comparison | Same 13 cases, only the model flipped. Haiku ~57% faster + ~66% cheaper and kept all 4 safety anchors; one consistent divergence (DC-12 nurse seniority: Haiku junior vs Sonnet mid). Saved side-by-side comparison report. | Done
6/7 | Dream Company | Stability (guardrail #1) | 3x repeat DC-10 + DC-12 on Haiku | Removed n=1 LLM variance risk. DC-10 entry 3/3 (honesty holds), DC-12 junior 3/3 - Haiku is stable, the seniority divergence is a consistent trait not noise. Meets PM's pass condition. | Done
6/7 | Dream Company | Model decision | Switch to Haiku 4.5 (PM approved + 3 guardrails) | PM approved the switch. Guardrail #1 (stability) done. Remaining: set LLM_MODEL_DREAM_COMPANY=claude-haiku-4-5-20251001 on Railway (env-flip = instant rollback) + Vi sign-off on the DC-12 seniority point. | In progress
| Dream Company / Job Source | Feature (config) | JS-0: Env flags + job-source config | Added DREAM_JOB_SOURCE flag (hybrid / adzuna_reed / exa), per-source timeout and 20-min cache TTL settings. Also set up the backend unit-test runner (node --test), which the project did not have before. | Done
| Dream Company / Job Source | Integration | JS-1 & JS-2: Adzuna + Reed API clients | Built two live-vacancy clients with a shared retry helper (429/5xx, backoff x3) and an 8s timeout. A missing API key returns a clean 503 that the orchestrator routes around instead of crashing. | Done
| Dream Company / Job Source | Feature (core) | JS-3: Routing + normalize + fallback orchestrator | New job-search service: routes by location (UK -> Adzuna+Reed, covered countries -> Adzuna, elsewhere -> Exa), converts results to the existing job shape, drops stale (>45d) and expired jobs, and falls back safely (source -> other source -> Exa -> clear "unavailable" message). Never throws, so the roadmap can never be taken down by a dead job source. | Done
| Dream Company / Job Source | Code fix | JS-4: Wire into Dream Company + show posted date | Routed the roadmap job search through the new orchestrator with the return shape unchanged (both streaming and non-streaming). With DREAM_JOB_SOURCE=exa the behaviour is identical to before. Added a "Posted N days ago" line to each job card. | Done
| Dream Company / Job Source | Feature | JS-5: Merge + dedupe + cache | Merge the two UK sources, remove duplicate postings by URL, keep the 20 newest, and cache results in-memory for 20 minutes to avoid repeat API calls (with free-tier rate limits in mind). | Done
| Dream Company / Job Source | Observability | JS-6: Cost / source logging | Added Adzuna/Reed call tracking (cost 0) and per-request logging of which source was used and whether the cache was hit. | Done
| Dream Company / Job Source | Testing | JS-7: Unit tests + live acceptance harness | 42 backend unit tests, all passing (routing, freshness filter, dedupe, cache, fallback, retry, both clients). Wrote a 13-case live harness that grades the success metrics: >=90% of jobs <=45 days old, 100% valid URLs, 0 LinkedIn profile links, plus an Exa-vs-hybrid comparison and a Vietnam fallback check. | Done (unit tests); live run pending API keys
| Dream Company / Job Source | Docs / Rollout | JS-8: Operations runbook | Wrote docs/JOB_SOURCE_RUNBOOK.md: staged rollout, 1-minute rollback via one env variable, how to read logs, free-tier limits, and API-key rotation. | Done (doc); Railway env flip + live harness pending
| Dream Company / Job Source | Deploy | Merged to main | Feature merged to main (so it is on production). Prod defaults to hybrid but, with no Adzuna/Reed keys set yet, it safely falls back to Exa (old behaviour). Recommended: set DREAM_JOB_SOURCE=exa on Railway until the live harness passes, then flip to hybrid. | Action needed
| Dream Company / Job Source | Investigation | Cross-check PM bug analysis vs code + prod logs | Violet re-test still saw stale/dead jobs after PR #13. Pulled Railway prod logs: a real London search showed Adzuna+Reed returning 0 results then falling back to Exa (source of the bad jobs). Verified all 6 PM findings (D1-D6) against the code line-by-line, and found a 7th root cause the analysis missed (D0). | Done
| Dream Company / Job Source | Bugfix (D0) | Fix over-broad job query (root cause of 0 results) | Query was joining ALL 7 selected role titles into one keyword string -> job boards required every word -> 0 matches -> silent Exa fallback. Now runs one query per top-3 roles and searches by city (e.g. "London") instead of "London, United Kingdom". Live QA: Adzuna/Reed now return 16-19 real jobs per search. | Done
| Dream Company / Job Source | Bugfix (D1+D2) | Freshness: never return unfiltered + hard 30-day cap | Old code returned the FULL unfiltered list (incl. months-old jobs) whenever <8 fresh jobs passed - the main cause of "posted months ago". Rewrote to widen the window 7->14->30 days only as needed and NEVER exceed a hard 30-day cap; window is env-configurable (default 7d, can tighten to 48h). | Done
| Dream Company / Job Source | Bugfix (D3) | Stop Exa fallback for UK profiles | UK searches with few/zero structured results were silently falling back to Exa (the source of dead links + LinkedIn profiles + wrong dates). Now UK/covered routes never use Exa; Exa is reserved only for genuinely uncovered locations. QA: 5/5 UK searches show source=uk, 0 from Exa. | Done
| Dream Company / Job Source | Bugfix (D4+D5) | Drop undated jobs + dead-link liveness check | D4: jobs without a real posting date are dropped so no blank/guessed dates show (exa=rollback mode kept byte-identical). D5: new liveness check HTTP-HEADs each URL and removes 404/410 dead links (fail-open on network error). QA: 0 undated jobs, 100% live links across all searches. | Done
| Dream Company / Job Source | Observability (D6) | Add sparse/confidence meta to results | Added meta {source, windowDaysUsed, sparse, checkedLinks} to the search result (jobs shape unchanged) so the UI can be honest about thin results and QA can assert behaviour. | Done
| Dream Company / Job Source | QA / Testing | 52 unit tests + live 5-search QA harness | Backend unit tests 52/52 pass; typecheck clean both sides. Ran the mandatory >=5 real UK searches (London/Manchester/Leeds/Remote): 100% jobs within window, 0 undated, 0 Exa, 100% live links. Exported COMPARISON-jobsource-fix.md as the QA log to attach for Violet. | Done
| Dream Company / Job Source | Release | Fix branch ready for PR | All changes on branch fix/job-source-freshness (backend + tests + QA harness + runbook). Pending: open PR + merge to main (auto-deploys Railway); Violet to confirm the freshness window number (default 7d, env-tunable to 48h). | In progress
| Dream Company / Job Source | Investigation | User-level verification: crawl real job links | Ran the FULL pipeline locally (LLM generates roles from a CV -> roadmap.jobs) and crawled the actual job links to judge quality. Found jobs are fresh (0-4 days) and links are live (verified DVSA Data Analyst, One Manchester Data Engineer are still hiring), but the date-sort surfaced some off-topic jobs at the top (e.g. "Legal Technologist"/"Data Administrator" for a Data Analyst search). Confirmed root cause is the job board keyword match, not the LLM roles (roles were accurate). | Done
| Dream Company / Job Source | Bugfix (Relevance A) | Adzuna title_only + deterministic relevance filter | PM chose the cheap deterministic fix (no extra LLM, no latency). Verified against the live Adzuna API that title_only restricts matches to the job TITLE (corrected the spec detail: it takes keywords, not a =1 flag). Added a filterByRoleRelevance step (head-token + supporting-token match, strips seniority words) after normalize, before freshness. Applies to Adzuna + Reed; Exa/rollback path untouched. | Done
| Dream Company / Job Source | Guardrail | Precision-first, no back-fill on thin results | Relevance filter is strict (precision over recall) and never relaxes: if it leaves few jobs it shows fewer + a sparse flag instead of padding with off-topic jobs (reuses the meta from the freshness fix). Adjacent roles (e.g. Data Engineer for a Data Analyst search) are intentionally dropped. | Done
| Dream Company / Job Source | QA / Testing | 59 unit tests + live 5-search before/after QA | Unit tests 59/59 pass incl. the PM AC2 relevance table + title_only param assertion; typecheck clean both sides. Ran 5 real UK searches: 0 off-topic jobs survived in every one (Accountant went from 15 off-topic to 0; Software Engineer dropped Structural/Civil Engineer noise). Exported COMPARISON-relevance-fix.md as the QA log for Violet. | Done
| Dream Company / Job Source | Release | Relevance fix branch ready for PR | On branch fix/job-source-relevance (Adzuna client + orchestrator + tests + QA harness). Pending: PR + merge (auto-deploys Railway), then verify 1 UK profile end-to-end on cvadvance.com and check prod logs (source=uk, relevance_dropped). Only report to Violet once that is green. Phase-2 option (LLM re-rank) deferred until measured necessary. | In progress
| Dream Company / Job Source | Investigation | Production test: crawl clicked job links | Tested on cvadvance.com with a Hong Kong profile and clicked through the returned job links. Found 3 problems: a "Scheduled Maintenance" page, a "job deleted" page, and a job whose location said Hanoi/Vietnam while the input was Hong Kong. Traced root cause in code: Hong Kong is outside our live-vacancy coverage so routeLocation fell back to Exa (the old web-search) - which returns wrong-location, deleted and soft-dead links. So that whole test ran on the old Exa path, not the new Adzuna/Reed pipeline. | Done
| Dream Company / Job Source | Bugfix (Issue 1) | Uncovered region -> honest notice, no Exa fallback | Per PM decision (a): stop falling back to Exa for uncovered locations. routeLocation now returns kind=unsupported for non-UK, non-Adzuna-covered regions; the orchestrator returns empty jobs + a benign NOTICE ("no direct live vacancies for {region}") - distinct from an error, so the roadmap still generates. Threaded the notice through 6 layers (backend types/service/RoadmapResponse -> FE type/hook/component); FE renders it as a soft blue info box, not a red error. Removed the now-dead Exa-hybrid path. This supersedes the old D3 "uncovered -> Exa" rule; VN also now shows the notice. | Done
| Dream Company / Job Source | Bugfix (Issue 2) | Dead-link check: status-only, skip Adzuna, bounded latency | Per PM: no content-scraping (slow/fragile). Layered defence - freshness (<=7d) is the primary shield, Reed expirationDate second, HTTP status-only third. Liveness now drops 404/410/5xx and expired-path redirects; SKIPS Adzuna URLs (bot-blocked, always 200 - rely on freshness); fail-open on timeout/network. Reordered pipeline to over-fetch then cap 20 AFTER the check so dropping dead links still fills a page. Measured Reed HEAD was slow (one case +6.4s) so tightened to a single parallel wave + 1.5s timeout -> avg latency +381ms (was failing >2s). Content-marker scan deferred (documented). | Done
| Dream Company / Job Source | QA / Testing | 64 unit tests + live latency QA | Unit tests 64/64 pass (routeLocation->unsupported, Hong Kong/VN notice, AC4 exa-mode, liveness 404/410/5xx + Adzuna-skip + fail-open + expired-URL, dedupeAndSort no-cap). Typecheck clean both sides. Live QA on 3 UK searches: all returned jobs, avg liveness latency +381ms (< 2s target). Exported COMPARISON-liveness.md. | Done
| Dream Company / Job Source | Release | Issues 1+2 committed, pending prod verify | Both fixes committed (2 commits) on the region/liveness branch. Pending: PR + merge (auto-deploys Railway), then verify on cvadvance.com - 1 UK profile (right-role jobs + live links) and 1 Hong Kong profile (blue notice, no wrong jobs); check prod logs (UK=source=uk, HK=route=unsupported). Rollback if needed: DREAM_JOB_SOURCE=exa. | In progress
| Dream Company / Job Source | Investigation | Why so few jobs? (filter funnel review) | User reported job counts feel low. Mapped the funnel: only the top 3 roles were searched (JOB_MAX_ROLE_QUERIES default 3), + strict relevance filter + 7-day freshness. Root issue for count: the role cap was a fixed 3, so picking 5 roles only searched 3. Confirmed all thresholds are env-configurable (code default used when Railway env not set), so freshness/role-count can be tuned without a deploy. | Done
| Dream Company / Job Source | Feature | Role cap: UI limit + backend source-of-truth + regenerate | Per PM 3-layer decision. (1) FE blocks selecting more than MAX (extra role cards disabled + "x/MAX selected" copy). (2) MAX is a single source of truth on the backend (JOB_MAX_ROLE_QUERIES, default raised 3->6) exposed via new GET /api/dream-company/config; FE reads it at runtime so a Railway env change updates the UI cap with no FE deploy. (3) Backend defense-in-depth: if a client sends > MAX it searches min(selected,MAX) and returns jobsTruncated=true (never silent) -> FE shows a soft notice. Search now covers exactly the selected count (<= MAX), ending "pick 5, search 3". | Done
| Dream Company / Job Source | UX fix | Add "Adjust roles & regenerate" (AC5 gap) | Found the roadmap screen was stuck after build: role cards froze and the only button was "Start New Search", so the PM copy "adjust your picks and regenerate" was not actually possible. Added an "Adjust roles & regenerate" button that returns to role selection keeping the analysis/roles, so the user can re-pick and rebuild; identical picks+location hit the in-memory cache (no extra API/rate-limit). | Done
| Dream Company / Job Source | QA / Testing | 64 unit tests + config endpoint runtime check | Unit tests 64/64 pass (topRoles = min(selected, MAX) incl. 8->6 and 2->2, default 6). Typecheck clean both sides. Booted backend locally: /api/health 200 and the new /api/dream-company/config returns 401 without a token (route registered + auth-protected, not 404). | Done
| Dream Company / Job Source | Release | Role-cap feature committed, pending prod verify | Committed on the region/liveness branch (backend config+route+service+types, FE proxy+client+hook+component). Pending PR + merge, then verify on cvadvance.com: try selecting >6 roles (blocked + counter), Adjust-roles-&-regenerate works. Tuning knobs live on Railway env (JOB_MAX_ROLE_QUERIES, JOB_FRESHNESS_MAX_DAYS) - change without deploy. MAX default = 6 (Violet can adjust). | In progress
| Dream Company / Job Source | Bug fix | No-jobs case sometimes showed nothing (Issue 1) | When a covered region returned 0 jobs after filtering, the UI showed neither jobs, error, nor notice - it went silent while the roadmap rendered. Added a benign notice ("couldn't find live vacancies for your roles in <location> right now") so all three empty cases always show a message. Notice flows job-search -> service -> hook -> existing blue notice box (no FE change). Typecheck clean; 66/66 backend tests pass (added 2). | Done
| Dream Company / Job Source | Feature / UX | Smarter location handling: gazetteer + LLM + radius (Issue 2) | Old router only matched literal country names / a few UK cities, so "Berlin", "San Francisco, CA" and typos all became "unsupported" (no jobs) even though covered. Built a hybrid resolver: (1) static city gazetteer (~120 major cities) as a fast, zero-cost path; (2) a cheap cached LLM fallback that maps free-text/misspelled locations to a supported country+city, constrained to the Adzuna set and fail-open (never blocks the flow, never falls back to Exa). Also added a search radius (JOB_SEARCH_RADIUS_KM, default 25km) on Adzuna+Reed to include nearby towns. Typecheck+build clean; 72/72 backend tests pass (added 6). | Done
| Dream Company / Job Source | UI fix | Roadmap "Skills to Build" pills overflowed the card (Issue 3) | Skills were rendered as nowrap pill Badges, but each skill is a long descriptive phrase, so the pills grew past the card's right border. Without touching the shared Badge component, changed just this section to wrapping rows: bold skill name + muted parenthetical detail, break-words + min-w-0 so it never overflows. Reads much cleaner than the dense yellow pills. Frontend typecheck clean (no new errors). | Done
27/7 | Candidate Acquisition (CA-001) | Scope decision | Self-decide the CA scope (no boss ask) | Investigated the 6 input sources and resolved the apparent 1003-vs-1005 contradiction: Project 1003 ("hiring audits") is B2B/employer-facing and belongs to Advance Acquisition, so once excluded 3/3 remaining sources point to (a) Academy students. Decided target = (c) both, prioritising (a). Wrote a Decision Record with assumptions + "wrong-if" conditions. Key insight: the capture "pipe" (table + endpoints) is safe regardless of a/b/c; only the specific lead-magnet copy is deferred. xlsx sources treated as reference-only (may be outdated). | Done
27/7 | Candidate Acquisition (CA-001) | Database | candidate_leads table + RLS (migration 012) | Created public.candidate_leads (email, name, source, lead_magnet_id, result jsonb, readiness_score, consent_marketing, consent_ts, double_optin, optin_token, utm_*, status). unique(email, source), email CHECK constraint, 3 indexes (email/status/optin_token). RLS enabled with a service_role-only grant and NO anon/authenticated grant (personal data). Applied by hand on Supabase + verified rowsecurity=true. | Done
27/7 | Candidate Acquisition (CA-001) | Backend | Lead-capture pipe (service + routes) | leads.service.ts: captureLead upserts by (email, source) non-destructively (never resets an existing opt-in, mints optin_token once); plus confirm/unsubscribe/list. Routes: POST /api/leads/capture (master switch LEADS_CAPTURE_ENABLED -> 404 when off, honeypot field, email/source validation, consent gate, 5/min per-IP rate-limit), GET /api/leads/confirm + POST /api/leads/unsubscribe (public, added to the auth skip-list). Backend typecheck clean; 6 curl cases pass exactly. | Done
27/7 | Candidate Acquisition (CA-001) | Integration | Wire the career quiz into the pipe | advance-academy-quiz: added an un-pre-ticked marketing-consent checkbox (UK GDPR/PECR) + Privacy Notice link, threaded consentMarketing through page/submit. /api/submit now pipes each submission to LEADS_CAPTURE_URL (source=quiz) best-effort and non-blocking, in parallel with the existing Google Sheet (a capture failure never blocks the user's result). Verified end-to-end: with consent -> confirm link logged + row; without consent -> row stored with consent_marketing=false and NO email. | Done
27/7 | Candidate Acquisition (CA-001) | Admin / Security | /admin/leads page + admin-only gate | Built the admin leads page (table + source/status filters + client-side CSV export) through the standard proxy -> backend-client -> Fastify chain. Security fix: GET /api/leads was only "authenticated", so any logged-in student could read personal data; added an ADMIN_USER_IDS allowlist (403 otherwise, fail-closed). Also fixed the frontend .env.local (missing NEXT_PUBLIC_SUPABASE_* was crashing the whole app). Typecheck clean both sides; tested admin sees the table + downloads CSV, non-admin gets 403. | Done
27/7 | Candidate Acquisition (CA-001) | Email | Double opt-in confirmation email via Resend | backend/src/lib/email.ts: Resend REST over fetch, 10s timeout, best-effort (never throws, so a mail hiccup cannot fail the capture request). sendConfirmEmail sends an HTML confirm email when EMAIL_API_KEY is set, else logs the link so the pipe stays testable without a provider. Tested live: a real confirm email is delivered and clicking Confirm flips double_optin=true / status=confirmed. Note: the default sender onboarding@resend.dev only delivers to the Resend account owner until a real domain is verified (documented for prod). | Done
27/7 | Candidate Acquisition (CA-001) | Deployment | Prod deploy runbook (handed to team for review) | Prepared the deploy steps: merge both repos (Railway backend + Vercel quiz/tools auto-deploy); Railway env (ADMIN_USER_IDS, LEADS_CAPTURE_ENABLED=true, APP_BASE_URL, EMAIL_API_KEY, EMAIL_FROM); Vercel quiz env (LEADS_CAPTURE_URL -> prod backend /api/leads/capture); confirm migration 012 on the prod Supabase project. Prod verification + feedback handed to another team. | In progress
28/7 | Candidate Acquisition (CA-001) | Frontend / Quiz | Quiz "reveal" step + template feedback (P1) | Chèn 1 bước hiển thị nhận xét giữa quiz và email: sau khi làm xong quiz hiện ngay đoạn nhận xét viết-sẵn theo nhóm (teaser/house, KHÔNG gọi LLM), rồi mới hiện ô nhập email để mở "full blueprint". Kết quả quiz được lưu vào candidate_leads.result. next build (quiz) pass. | Done
28/7 | Candidate Acquisition (CA-001) | Backend / Admin | UTM channel attribution (P3a) | Quiz đọc utm_* (và ref) từ URL rồi gửi kèm khi capture. listLeads + route /api/leads bổ sung cột utm_source + lọc theo utm_source + thêm cột vào CSV. Trang admin thêm cột "Channel" + ô lọc kênh (free-text) + cột trong CSV. Backend + frontend + quiz typecheck sạch. | Done
28/7 | Candidate Acquisition (CA-001) | Auth | Passwordless magic-link login (P2a/2b) | Backend service tạo tài khoản (admin.createUser mật khẩu ngẫu nhiên, dedup email trùng) + gửi magic link. Delivery dùng magic link BUILT-IN của Supabase (signInWithOtp, gửi được mọi email, không cần domain) — fallback in link ra console cho dev. Trang /auth/callback nhận session + set cookie aa-session; middleware mở public /auth/callback. Register chuyển passwordless (chỉ email); Login GIỮ mật khẩu + thêm nút "email me a login link" (học viên cũ không bị ảnh hưởng). Quiz nhập email (consent) tự tạo trial account + gửi magic link. | Done
28/7 | Candidate Acquisition (CA-001) | Backend / Quota | Trial tier + lifetime tool quotas (P2c) | Migration 013: cột users.tier (default "student" = fail-open, học viên cũ full quyền) + bảng trial_usage (RLS on, backend-only). Helper trial-quota.ts chặn theo hạn mức TRỌN ĐỜI (không reset ngày): CV 1 / Dream 2 / Interview 1 (env TRIAL_TOTAL_*). Gắn gate vào 3 tool (CV Optimizer, Dream Company, Interview) — chặn 429 khi hết lượt. Cơ chế đếm bền (Supabase) tách biệt và cộng hưởng với perUserDaily có sẵn. Backend typecheck sạch. | Done
28/7 | Candidate Acquisition (CA-001) | Backend / Frontend | Referral loop + activation credits (P3c) | Migration 014: users.referral_code / referred_by / referral_credited / referral_count + trial_usage.bonus_count. Mỗi user 1 mã mời; trang /referral hiện link mời, tiến độ, và CTA Mentorship khi đạt cap 3. Người được mời gắn referred_by lúc signup; inviter được +2 Dream credit CHỈ khi invitee DÙNG TOOL lần đầu (activation = login + dùng ≥1 tool) — chốt cứng trong hàm credit, chống tự-mời/email-giả, idempotent, cap 3 lượt. Backend + frontend typecheck sạch. | Done
28/7 | Candidate Acquisition (CA-001) | Frontend / Quiz | Share result button (P3b) | Nút "Share my result" ở trang kết quả quiz: dùng Web Share API (mobile) / copy clipboard (desktop), link gắn utm_source=share. Nâng cấp "khoe kết quả trong link + ảnh preview OG (Lớp 2)" đã thống nhất làm sau. | Done
28/7 | Candidate Acquisition (CA-001) | Ops / Config | Local end-to-end verify + Supabase/env config | Áp migrations 006/013/014. Bật Supabase "Allow new users to sign up" (fix lỗi "Signups not allowed for otp") + thêm SUPABASE_ANON_KEY fallback cho OTP + allowlist Redirect URL /auth/callback. Gỡ rối env: dev đọc file .env, prod đọc dashboard Railway/Vercel (đã lập bảng ánh xạ). Map domain prod: quiz.cvadvance.com + www.cvadvance.com. Deploy prod (D1–D5) chờ Railway còn usage; test local các luồng chính. | In progress